## TASKS
Project Timeline
No | MY TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
1 | Understanding the Project topic | 2016-11-10 | 2016-11-10 | 100% | 100%
2 | Studying the DD and EMDD algorithms | 2016-11-10 | 2016-11-11 | 100% | 100% | Goal achieved
3 | Implementing EMDD in python | 2016-11-11 | 2016-11-18 | 75% | 0 | In progress
4 | Matlab setup for other state-of-art MIL algorithms | 2016-11-11 | 2016-11-11 | 100% | 1 | Goal achieved
5 | Obaining implementation results for MIL public datasets musk1, musk2, Elephant, Fox and Tiger, COREL | 2016-11-16 | 2016-11-24 | 0% | 0 | In progress
6 | Analyze the results obtained and corner cases | 2016-11-16 | 2016-11-24 | 0% | 0 | In progress
7 | Result comparison for Synthetic data set against EMDD and state-of-art | 2016-11-24 | 2016-11-25 | 0% | 0 | Strech goal
8 | Investigating other methods that solve MIL problems and compare them with EMDD | 2016-11-25 | 2016-11-30 | 0% | 0 | Strech goal
|  |  | Overall Progress | 60% | 0